## Project level
Task | Subtast | Owner | Progress
Class Diagram |  | Shubham Garg | done
ER diagram |  | Shubham Gupta | done
SQL/DB structure |  | Preyashi | done
Architecture Diagram |  | Shivasai | done
Cohort 1 repo | Test Scenario |  | done
| Diagrams(Block, sequence) |  | done
| Api Service |  | done
| Test(unit, integration) |  | done
| Postman SS |  | done
| Push code and diagram to repo |  | done
Cohort 2 repo | Test Scenario |  | done
| Diagrams(Block, sequence) |  | done
| Api Service |  | done
| Test(unit, integration) |  | done
| Postman SS |  | done
| Push code and diagram to repo |  | done
Cohort 3 repo | Test Scenario |  | done
| Diagrams(Block, sequence) |  | done
| Api Service |  | done
| Test(unit, integration) |  | done
| Postman SS |  | done
| Push code and diagram to repo |  | done
Cohort 4 Repo | Test Scenario |  | done
| Diagrams(Block, sequence) |  | done
| Api Service |  | done
| Test(unit, integration) |  | done
| Postman SS |  | done
| Push code and diagram to repo |  | done

## cohort1
S No. | Action | Cohort/person | AssignedOn | Deliverby | Status
1 | Architecture diagram | Shubham |  | 31/08/2020 | done
2 | sequence diagram | Tanmay |  | 31/08/2020 | done
3 | SQL/DB structure | preyashi |  | 29/08/2020 | done
4 | Test Scenarios | shubham/preyashi |  | 31/08/2020 | done
5 | matchingcompany | preyashi |  | 28/08/2020 | done
6 | comparecompany | preyashi |  | 29/08/2020 | done
7 | ipo(get/add/update/delete/getbycompname) | shubham |  | 29/08/2020 | done
8 | company(get/add/update/delete) | tanmay |  | 29/08/2020 | done
9 | Integrated code | preyashi |  | 30/08/2020 | done
10 | Unit test cases | shubham/preyashi |  | 30/08/2020 | done
11 | Integrated test cases | preyashi |  | 30/08/2020 | done
12 | postman screenshots | preyashi |  | 31/08/2020 | done

## cohort2
S No. | Action | Cohort/person | AssignedOn | Deliverby | Status
| Microservice 4 | Sowmya and Amlan
1 | Architecture diagram | amlan |  | 31st | done
2 | sequence diagram | sowmya |  | 31st | done
3 | SQL files | sowmya |  | 31st | done
4 | Test Scenarios | sowmya, amlan |  | 31st | done
5 | Class Diagram | amlan |  | 31st | done
6 | Integrated code | amlan, sowmya |  | 31st | done
7 | Unit test cases | amlan, sowmya |  | 31st
8 | Integrated test cases | not clear
9 | postman screenshots | sowmya |  | 31st | done
| Microservice 5 | Shubham Gupta
1 | Architecture diagram | Shubham Gupta |  | 31/08/2020 | done
2 | sequence diagram | Shubham Gupta |  | 31/08/2020 | done
3 | SQL files | Shubham Gupta |  | 31/08/2020 | done
4 | Test Scenarios | Shubham Gupta |  | 31/08/2020 | done
6 | Integrated code | Shubham Gupta |  | 31/08/2020 | done
7 | Unit test cases | Shubham Gupta |  | 31/08/2020 | done
8 | Integrated test cases | Shubham Gupta |  | 31/08/2020 | -
9 | Postman screenshots | Shubham Gupta |  | 31/08/2020 | done

## cohort3
S No. | Action (Milestone 1) | Cohort/person | AssignedOn | Deliverby | Status
1 | Architecture diagram | Siddhanth |  | 31/08/2020 | done
2 | sequence diagram | Siddhanth |  | 31/08/2020 | done
3 | SQL files | Arnapurna |  | 31/08/2020 | done
4 | Test Scenarios | All |  | 31/08/2020 | done
6 | Integrated code | Arnapurna |  | 31/08/2020 | done
7 | Unit test cases | Ankit |  | 31/08/2020 | done
8 | Integrated test cases | Ankit |  | 31/08/2020 | done
9 | postman screenshots | Arnapurna |  | 31/08/2020 | done
10 | Microservice 1 Basic Fuctioning code | All |  | 30/08/2020 | done

## cohort4
S No. | Action | Cohort/person | AssignedOn | Deliverby | Status
1 | Architecture diagram | Ashish |  | 31/8/20 | Done
2 | sequence diagram | Ashish |  | 31/8/20 | Done
3 | SQL files | Ishaan |  | 31/8/20 | Done
4 | Test Scenarios | Shivasai |  | 31/8/20 | Done
5 | Integrated code | Ashish |  | 31/8/20 | Done
6 | Unit test cases | Ishaan |  | 31/8/20 | Done
7 | Integrated test cases | Ishaan |  | 31/8/20 | Done
8 | postman screenshots | Ashish |  | 31/8/20 | Done
9 | Api Controller methods | Ashish and Ishaan |  | 31/8/20 | Done
10 | sectors(get/add/delete) | Ashish and Ishaan |  | 31/8/20 | Done
11 | functionality with other microservices | Ashish |  | 31/8/20 | Done